## App Structure
Item | Requirement type | Objective | How it helps you & the team
By Person | Enhance existing — highest priority | Add days-in-current-status and last-activity per story, pulled from Jira changelog (not the due-date field), plus a visible "stale" flag | This is the page that actually fixes daily scrum: instead of "I've been working on it," the ticket's own history shows how long it's really sat — same data for everyone, no PM needed to police it
Portfolio Summary | Enhance existing — data honesty fix | Relabel the Run/Change split so the 0% Run segment reads "Run work not yet tracked" instead of implying there is none | Keeps the executive view from silently overstating completeness — matches the "Not tracked in JIRA" honesty already used elsewhere in the app
Work Explorer | Enhance existing — minor | Turn the existing "no due date" / "overdue" tags into filters, not just labels | Lets anyone isolate exactly the stale or undated work without hunting through 152 stories manually
Ask the Data | Enhance existing — expand into two modes | Add a "Create" mode alongside the existing "Ask" mode: plain-language input → GenAI drafts title, acceptance criteria, epic match, sub-tasks → human reviews → creates in Jira | Removes the create-a-story form entirely; one chat surface does both querying the portfolio and drafting new work, and standardizes acceptance criteria without needing a scrum master
Create / Update Story (placeholder) | Merge — do not build standalone | Fold into Ask the Data's new "Create" mode rather than building a separate page | Avoids building two UIs that do the same kind of interaction; one surface to maintain
Capacity (placeholder) | New — sequence after By Person | Aggregate the per-person aging/status data into team-level allocation once it's trustworthy | Becomes an accurate rollup instead of a nicer-looking version of today's incomplete picture
Customer Support (placeholder) | Hold — sequence after Capacity | Reserved for INC/ITSR intake; rename to something literal like "Run work" when built | Keeps run work (support/incident time) visible against the same 15 people, once the data source question is resolved
JIRA Management + Export / Analysis + Refresh / Status (placeholders) | Consolidate into one page | Combine board/project config and admin settings, data export/analysis, and sync status (last refresh, data health) into a single admin/utility page | One page for all tool housekeeping — config, exports, and sync status — keeps the top-level nav focused on work views instead of admin utilities